Department of Information Technology

Faculty of Computing

Software Management-SE4111

Risk Management - Tutorial

M.A.K.A Masinghe

F20011006013

IT_IFLS_001/B003/0030

- Draw the full decision tree for this scenario. Your diagram must include: the decision node, both chance nodes, all four end nodes, branch labels showing probabilities and costs, and the correct node symbols (square, circle, diamond).

- Calculate the EMV for each option, showing full working. Remember to include the upfront cost in each total outcome value before applying probabilities.

Option 1: External Penetration Testing Firm

Outcome 1 : System Passes

35,000+0=35,000

Outcome 2 : Vulnerabilities Found

35,000+40,000=75,000

EMV

EMV= (0.60×35,000)+(0.40×75,000)

EMV= 21,000+30,000

EMV= $51,000

Option 2: Internal QA Team

Outcome 1 : All Vulnerabilities Detected

15,000+20,000=35,000

Outcome 2: Vulnerabilities Missed

15,000+150,000=165,000

EMV

EMV= (0.35×35,000)+(0.65×165,000)

EMV=12,250+107,250

EMV=$119,500

- State which option the decision tree recommends and identify the option the PM should actually choose

The PM should also choose Option 1 (External Penetration Testing Firm) because:

- It has the lowest expected cost.

- It significantly reduces the likelihood of a post-launch security breach.

- A hospital system handles sensitive patient data.

- A breach could cause:

  - Regulatory fines

  - Legal liability

  - Reputational damage

  - Loss of patient trust

  - Service disruption during emergencies

Therefore, both the decision tree analysis and practical risk management considerations support choosing Option 1 – External Penetration Testing Firm.