Department of Information Technology

Faculty of Computing

Software Management-SE4111

Risk Management - Tutorial

M.A.K.A Masinghe

F20011006013

IT_IFLS_001/B003/0030

- Complete a full risk register entry for each of the four risks raised in the meeting (vendor API, key developer departure, regulatory change, infrastructure failure). Use the template provided. All 11 fields must be completed for each risk.

| Field | Value |
| --- | --- |
| Risk ID | R001 |
| Risk Title | Vendor API Integration Failure |
| Description | Third-party API may fail, causing inability to exchange patient and emergency data. |
| Category | Technical |
| Cause | Vendor system instability or API changes |
| Consequence | System integration delays and service disruption |
| Probability | 4 (Likely) |
| Impact | 5 (Critical) |
| Risk Score | 20 |
| Response Strategy | Mitigate |
| Mitigation Action | Create backup API, conduct early integration testing, establish SLA with vendor |
| Risk Owner | Technical Lead |

| Field | Value |
| --- | --- |
| Risk ID | R002 |
| Risk Title | Key Developer Leaves Project |
| Description | Lead developer resigns during development. |
| Category | Human Resource |
| Cause | Better job opportunity, personal reasons |
| Consequence | Knowledge loss, schedule delays |
| Probability | 3 (Possible) |
| Impact | 4 (Major) |
| Risk Score | 12 |
| Response Strategy | Mitigate |
| Mitigation Action | Documentation, code reviews, knowledge sharing sessions |
| Risk Owner | Project Manager |

| Field | Value |
| --- | --- |
| Risk ID | R003 |
| Risk Title | Healthcare Regulatory Changes |
| Description | Government introduces new healthcare data protection regulations. |
| Category | Legal / Compliance |
| Cause | Policy updates |
| Consequence | System redesign and compliance costs |
| Probability | 3 (Possible) |
| Impact | 5 (Critical) |
| Risk Score | 15 |
| Response Strategy | Mitigate |
| Mitigation Action | Monitor regulations and involve compliance specialists |
| Risk Owner | Compliance Manager |

| Field | Value |
| --- | --- |
| Risk ID | R004 |
| Risk Title | Infrastructure or Server Failure |
| Description | Hardware, network, or cloud infrastructure failure causes system downtime. |
| Category | Infrastructure |
| Cause | Power outage, hardware failure, network outage |
| Consequence | Emergency doctors lose access to patient information |
| Probability | 4 (Likely) |
| Impact | 5 (Critical) |
| Risk Score | 20 |
| Response Strategy | Mitigate |
| Mitigation Action | Redundant servers, disaster recovery plan, backups |
| Risk Owner | Infrastructure Manager |

- Rank the four risks from highest to lowest priority based on their risk scores. Where two risks have the same score, justify which should be treated first and why, with reference to the nature of the system.

| Rank | Risk | Score |
| --- | --- | --- |
| 1 | Infrastructure Failure | 20 |
| 2 | Vendor API Failure | 20 |
| 3 | Regulatory Change | 15 |
| 4 | Key Developer Departure | 12 |

Justification

Although Infrastructure Failure and Vendor API Failure both score 20, Infrastructure Failure should be treated first because SHERS is an emergency healthcare system.

If infrastructure fails:

- Real-time patient monitoring stops.

- Emergency doctors lose EMR access.

- Patient safety is immediately affected.

Vendor API issues are serious but usually affect only certain integrations rather than the entire system.

Therefore:

Infrastructure Failure > Vendor API Failure > Regulatory Change > Key Developer Departure

- For the highest-scoring risk only, identify one additional secondary risk that could arise if the primary risk's mitigation action fails. Write a brief risk register entry (description, probability, impact, score, response) for this secondary risk.

Primary Risk: Infrastructure Failure

Secondary Risk:

| Field | Value |
| --- | --- |
| Description | Complete loss of patient monitoring data due to backup system failure during infrastructure outage |
| Probability | 3 |
| Impact | 5 |
| Risk Score | 15 |
| Response | Implement off-site backups, disaster recovery testing, and failover systems |

- Kavindi's sponsor says: "We don't have time for all this documentation. Just deal with problems when they come up." Write a brief response (3–4 sentences) that Kavindi could give to justify why a formal risk register is essential for this project specifically.

"Kavindi could respond:"

The SHERS project supports emergency medical services where system failures can directly affect patient safety. A formal risk register helps us identify, prioritize, and prepare for risks before they become costly problems. Managing risks proactively reduces delays, regulatory issues, and service interruptions. Without a risk register, the project team may react too late to critical issues that could impact hospital operations and patient care.